## Trang tính1
Task name | Page (or components) | Start Build | Finish Build | Names | Note
Wireframe
login |  |  |  | Phong
register |  |  |  | Đạt
index |  |  |  | Phong
index (khi hover vào các component hàng members) |  |  |  | Phong
projectDetail |  |  |  | Đạt
createProject |  |  |  | Phong
createTask ( giao diện giống editTask) |  |  |  | Đạt
comment |  |  |  | Đạt
Dựng layout
login |  |  |  | Phong | done
register |  |  |  | Đạt
sideBar |  |  |  | Phong | done
index |  |  |  | Phong | done
projectDetail |  |  |  | Đạt
createProject |  |  |  | Phong
createTask |  |  |  | Đạt | done
taskDetail (có comment) |  |  |  | Đạt
editTask |  |  |  | Đạt | done
Dựng tính năng
signup | register |  |  | Đạt
signin | login |  |  | Phong
getAllProject | index (call ngay vừa vừa load trang)
getUserByProjectId | index (hàng member)
getProjectDetail | index (hàng action) => chuyển sang page detail
deleteProject | index (hàng action)
updateProject | projectDetail
removeUserFromProject | index (hàng member)
getUserByProjectId | index (trong từng component hàng member)
assignUserProject | index (trong từng component hàng member)
removeUserFromProject | index (trong từng component hàng member)
createProjectAuthorize | createProject
ProjectCategory | createProject
getAllProject | createTask
Status/getAll | createTask
Priority/getAll | createTask
TaskType/getAll | createTask
/Users/getUser | createTask
Project/assignUserTask | createTask
getTaskDetail | editTask
updateTask | editTask
4 tính năng phần comment | comment
Khác
khởi tạo các file dự án |  |  |  | Phong | done
deploy |  |  |  | Phong
youtube |  |  |  | Phong
Link figma: | https://www.figma.com/file/0uzR7PPCe9IwqFr3Jv14eX/JIRA_PROJECT?type=design&node-id=0%3A1&mode=design&t=ARkaj4Z4vhf0jfM6-1
Link mô tả dự án: | https://drive.google.com/drive/folders/1WUpiEhcBU1raigfMNgew3EKctC5c4B34
Dán link youtube:
Dán link deloy:
Dán link github:
Link api: | https://jiranew.cybersoft.edu.vn/swagger/index.html